## Slide 1: Sustainable airport master plan near term projects environmental review update
Susan Cezar, Chief Strategic Officer
June 23, 2022

## Slide 2: History
2015-2018
Port of Seattle completed the Sustainable Airport Master Plan (SAMP)
  Issued Determination of Significance/Scoping Notice and completed scoping for the Near Term Projects (NTP) environmental review
2018
City of Des Moines entered into an inter-local agreement with the cities of Burien, Normandy Park and SeaTac for coordination on review of the environmental documents
The four cities contracted with expert consultants to assist with the review
The combined cities submitted scoping comments and Des Moines also submitted separate comments
2020
  Cities updated the inter-local agreement transferring administration to Des Moines
2021
Amended consultant contract to extend the date and add funds

## Slide 3: Monitoring
City staff continue to attend meetings and keep up to date related to SAMP NTP environmental review
Keep in contact with consultants and other cities to prepare for issuance and comment period
City is monitoring compliance with National Environmental Policy Act (NEPA)/State Environmental Policy Act (SEPA) requirements as the Port has proceeded with capital projects

## Slide 4: Timeline and process
Port of Seattle/FAA Original Plan for NTP environmental review:
Combined environmental document – SEPA Environmental Impact Statement (EIS) and NEPA Environmental Assessment (EA)
Process was to be complete in Winter 2019
Port of Seattle/FAA Current Plan:
Issuance of NEPA EA and SEPA EIS as separate documents
EA issuance first for public comment – target date was October 2022, now delayed to 2023
SEPA EIS will follow at an undetermined date
According to the Port, schedule has been delayed by Covid, work load/retirements, updating planning information, agency consultation, need for additional analysis

## Slide 5: Next steps
Once EA is issued, coordinate with consultants and other cities for joint comments
Comments specific to Des Moines if needed
Anticipated EA issuance in 2023
SEPA EIS will follow a similar process once issued - schedule undetermined
Transition - Community Development Director Denise Lathrop will be involved going forward

## Slide 7: Consultants
Primacy Strategy Group LLC
https://primacysg.com/
ABCx2
www.abcx2.com